## Effort Estimation
SL# | Activities | % | PM | CM | AR | TL | SD | JD | TM | ST | JT | TW | RC | 1R | Effort Man-days | Effort Man-Months | Approx Timeline days
1 | Requirement Analysis | 8.682% |  | 3 | 0 | 6 | 6 | 0 | 2.5 | 0.5 | 0 | 0 | 18 |  | 57 | 2.85 | 3.1667
| Functional |  |  |  |  | 1 | 1 |  | 0.5 | 0.5 |  |  | 3 | 10 | 30
Non-Functional
| Existing Technology landscape |  |  | 1 |  | 1 | 1 | [5 empty] | 3 | 3 | 9
| SSO |  |  | 0.5 |  | 1 | 1 | [5 empty] | 2.5 | 1 | 2.5
| Remote Access thru VPN |  |  | 0.5 |  | 1 | 1 | [5 empty] | 2.5 | 2 | 5
| Performance SLA |  |  | 0.5 |  | 1 | 1 |  | 1 |  |  |  | 3.5 | 1 | 3.5
| User Privilege & security |  |  | 0.5 |  | 1 | 1 |  | 1 |  |  |  | 3.5 | 2 | 7
2 | Design & Development | 100% |  | 4 | 3 | 39 | 48.5 | 41.5 | 3.5 | 2 | 0 | 0 | 141.5 |  | 656.5 | 32.825 | 50.9102
1 | Design & Configuration | 16.07% |  | 4 | 0 | 4 | 4 | 0 | 3.5 | 2 | 0 | 0 | 17.5 |  | 105.5 | 5.275 | 6.0286
| Environment setup & Configuration |  |  | 1 |  | 1 | 1 |  | 1 |  |  |  | 4 | 7 | 28
| User Privilege & security Design/Setup |  |  | 1 |  | 1 | 1 |  | 0.5 |  |  |  | 3.5 | 5 | 17.5
| Solution Design & Framework |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 5 | 7 | 35
| Mobile Design & Framework |  |  | 1 |  | 1 | 1 |  | 1 | 1 |  |  | 5 | 5 | 25
2 | Manages Uniform Inventory |  |  | 0 | 1 | 2 | 5 | 4 | 0 | 0 | 0 | 0 | 12 |  | 66 | 3.3 | 5.5
| CRUD Uniform Inventory |  |  |  | 0.5 | 0.25 | 1 | 1 |  |  |  |  | 2.75 | 7 | 19.25
| CRUD Uniform Inventory Service |  |  |  |  | 0.25 | 1 | 1 |  |  |  |  | 2.25 | 3 | 6.75
| Inventory Dashboard |  |  |  |  | 0.5 | 1 | 1 |  |  |  |  | 2.5 | 5 | 12.5
| Inventory Lookup Service (Taxonomy based) | [5 empty] | 1 | 1 |  |  |  |  | 2 | 5 | 10
| Inventory Lookup Service (Free text search) - optional |  |  |  | 0.5 | 1 | 1 | [5 empty] | 2.5 | 7 | 17.5
3 | RFID or Barcode inventory tracking |  |  | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 4 |  | 16 | 0.8 | 4
| Inventory Tracking by RFID |  |  |  |  | 0.5 | 0.5 | 1 |  |  |  |  | 2 | 5 | 10
| Inventory Tracking by Barcode |  |  |  |  | 0.5 | 0.5 | 1 |  |  |  |  | 2 | 3 | 6
4 | Manages Employees Uniform entitlements |  |  | 0 | 0 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 5 |  | 27 | 1.35 | 5.4
| CRUD Employee Uniform entitlement |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 7 | 21
| CRUD Employee Uniform entitlement Service | [5 empty] | 1 | 1 |  |  |  |  | 2 | 3 | 6
5 | Track Laundry Activities and Wash cycles |  |  | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 15 |  | 75 | 3.75 | 5
| CRUD Laundry Activities |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 7 | 21
| Inventory-Laundry Mapping |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| CRUD Laundry Activities Services |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 3 | 9
| Laundry Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Track Laundry Activities and Wash cycles |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
6 | Generates replenishment orders |  |  | 0 | 0 | 4 | 6.5 | 7.5 | 0 | 0 | 0 | 0 | 18 |  | 58.5 | 2.925 | 3.25
| Replenishment order rules |  |  |  |  | 1 | 1 | 0.5 |  |  |  |  | 2.5 | 5 | 12.5
| Automatic order service call |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Semi-automatic order service call |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 3 | 9
| Order Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 3 | 9
| Track Order Status | [5 empty] | 1 | 1 |  |  |  |  | 2 | 2 | 4
| Track orders in process | [5 empty] | 0.5 | 1 |  |  |  |  | 1.5 | 2 | 3
| Track lead-time | [5 empty] | 0.5 | 1 |  |  |  |  | 1.5 | 2 | 3
| Track Shipping | [5 empty] | 0.5 | 1 |  |  |  |  | 1.5 | 2 | 3
7 | Forecasts Uniform Purchases |  |  | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 5 |  | 25 | 1.25 | 5
| Forecast Rules |  |  |  |  | 1 | 1 | [5 empty] | 2 | 5 | 10
| Forecast Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
8 | System Integrations |  |  | 0 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 10 |  | 50 | 2.5 | 5
| Order service Integration |  |  |  | 0.5 | 1 | 1 | [5 empty] | 2.5 | 5 | 12.5
| HRMS Service Integration |  |  |  | 0.5 | 1 | 1 | [5 empty] | 2.5 | 5 | 12.5
| External Laundry Service Integration |  |  |  | 0.5 | 1 | 1 | [5 empty] | 2.5 | 5 | 12.5
| External Shipping service |  |  |  | 0.5 | 1 | 1 | [5 empty] | 2.5 | 5 | 12.5
9 | End users ability to make requests through the system |  |  | 0 | 0 | 0.5 | 2 | 3 | 0 | 0 | 0 | 0 | 5.5 |  | 20 | 1 | 3.6364
| CRUD User Service request |  |  |  |  | 0.5 | 1 | 1 |  |  |  |  | 2.5 | 5 | 12.5
| Service Request Dashboard | [5 empty] | 0.5 | 1 |  |  |  |  | 1.5 | 3 | 4.5
| Track User Service request | [5 empty] | 0.5 | 1 |  |  |  |  | 1.5 | 2 | 3
10 | Defines working groups and manages entitlement |  |  | 0 | 0 | 1.5 | 3 | 3 | 0 | 0 | 0 | 0 | 7.5 |  | 27.5 | 1.375 | 3.6667
| CRUD working groups |  |  |  |  | 0.5 | 1 | 1 |  |  |  |  | 2.5 | 5 | 12.5
| CRUD entitlement |  |  |  |  | 0.5 | 1 | 1 |  |  |  |  | 2.5 | 3 | 7.5
| Working group Dashboard |  |  |  |  | 0.5 | 1 | 1 |  |  |  |  | 2.5 | 3 | 7.5
11 | App based Services for Mobile users |  |  | 0 | 0 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 42 |  | 186 | 9.3 | 4.4286
| Inventory Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Inventory Tracking by RFID |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Inventory Tracking by Barcode |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Laundry Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Track Laundry Activities and Wash cycles |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Order Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Track Order Status |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Track orders in process |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Track lead-time |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Track Shipping |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Forecast Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Service Request Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 5 | 15
| Track User Service request |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
| Working group Dashboard |  |  |  |  | 1 | 1 | 1 |  |  |  |  | 3 | 4 | 12
3 | Testing | 23.61% |  | 0 | 0 | 1.5 | 0 | 0 | 3 | 3 | 8 | 0 | 15.5 |  | 155 | 7.75 | 10
| Functional |  |  |  |  | 0.5 |  |  | 1 | 1 | 3 |  | 5.5 | 10 | 55
| E2E Testing |  |  |  |  | 0.5 |  |  | 1 | 1 | 3 |  | 5.5 | 10 | 55
| Mobile based Testing |  |  |  |  | 0.5 |  |  | 1 | 1 | 2 |  | 4.5 | 10 | 45
4 | UAT | 21.63% |  | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 17 |  | 142 | 7.1 | 8.3529
| UAT Configuration & deployment |  |  | 1 |  | 1 | 1 | [5 empty] | 3 | 3 | 9
| UAT Support |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 7 | 14 | 98
| UAT Bug fixing |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 7 | 5 | 35
5 | Documentation & Training | 12.95% |  | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 2 | 6 |  | 85 | 4.25 | 14.1667
| Technical Documentation | [7 empty] | 0.5 | 1 |  | 1 | 2.5 | 15 | 37.5
| User Manual | [7 empty] | 0.5 | 1 |  | 1 | 2.5 | 15 | 37.5
| User Training | [7 empty] | 1 |  |  |  | 1 | 10 | 10
6 | Delivery & Deployment | 2.133% |  | 2 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 9 |  | 14 | 0.7 | 1.5556
| Production planning & configuration |  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | 2 | 10
| Go Live |  |  | 1 |  | 1 | 1 | 1 |  |  |  |  | 4 | 1 | 4
7 | Post Go Live Support (2 Weeks) | 14.93% |  | 0 | 0 | 1 | 1 | 2 | 0 | 1 | 2 | 0 | 7 |  | 98 | 4.9 | 14
[6 empty] | 1 | 1 | 2 |  | 1 | 2 |  | 7 | 14 | 98
| Total Effort w/o PM | [13 empty] | 1207.5
8 | Project Management | 8% | [10 empty] | 1 |  | 96.6 | 4.83 | 96.6
| Total Effort |  | 96.6 | 55 | 19 | 261 | 279.5 | 222.5 | 103.5 | 110 | 127 | 30 | 10.5 |  | 1304.1 | 65.205 | 198.752
[16 empty] | 6.21 | 9.9376
Note on D1: Project Manager
Note on E1: Configuration Manager
Note on F1: Architect / DB Modeler
Note on G1: Tech Lead
Note on H1: Sr. Developer
Note on I1: Jr. Developer
Note on J1: Test Manager / Lead
Note on K1: Sr. Tester
Note on L1: Jr. Tester
Note on M1: Technical Writer
Note on N1: Total Resource Count
Note on O1: Estimated Effort in days
Note on N109: Average Resource Count

## Resource Loading
Grade | Roles | Count | Effort Man-days | Effort Man-month | Onsite% | Offshore Effort | Onsite Effort | Row Labels | Total Offshore | Total Onsite
IS3 | Configuration Manager (CM) | 0.2 | 55 | 2.75 | 15% | 2.3375 | 0.4125 | IS1 | 17.2275 | 1.7475
IS4 | Architect (AR) | 0.25 | 19 | 0.95 | 10% | 0.855 | 0.095 | IS2 | 16.13 | 3.345
IS3 | Tech Lead (TL) | 1 | 261 | 13.05 | 20% | 10.44 | 2.61 | IS3 | 17.1763 | 3.7988
IS2 | Sr. Developer (SD) | 1 | 279.5 | 13.975 | 20% | 11.18 | 2.795 | IS4 | 0.855 | 0.095
IS1 | Jr. Developer (JD) | 3 | 222.5 | 11.125 | 10% | 10.0125 | 1.1125 | IS5 | 3.864 | 0.966
IS3 | Test Manager/Lead | 0.5 | 103.5 | 5.175 | 15% | 4.3987 | 0.77625 | Grand Total | 55.2527 | 9.9522
IS2 | Sr. Tester (ST) | 1 | 110 | 5.5 | 10% | 4.95 | 0.55
IS1 | Jr. Tester (JT) | 3 | 127 | 6.35 | 10% | 5.715 | 0.635
IS1 | Technical Writer (TW) | 0.25 | 30 | 1.5 | 0% | 1.5 | 0
IS5 | Project Manager | 1 | 96.6 | 4.83 | 20% | 3.864 | 0.966
Grand Total |  | 11.2 | 1304.1 | 65.205 | 15.26% | 55.2527 | 9.9522
Note on C2: Configuration Manager
Note on C3: Architect / DB Modeler
Note on C4: Tech Lead
Note on C5: Sr. Developer
Note on C6: Jr. Developer
Note on C7: Test Manager / Lead
Note on C8: Sr. Tester
Note on C9: Jr. Tester
Note on C10: Technical Writer
Note on C11: Project Manager

## Timeline
|  | Activity/Module |  |  | Effort | WK-0 | WK-1 | WK-2 | WK-3 | WK-4 | WK-5 | WK-6 | WK-7 | WK-8 | WK-9 | WK-10 | WK-11 | WK-12 | WK-13 | WK-14 | WK-15 | WK-16 | WK-17 | WK-18 | WK-19 | WK-20 | WK-21 | WK-22 | WK-23 | WK-24 | WK-25 | WK-26 | WK-27 | WK-28 | WK-29 | WK-30 | WK-31 | WK-32 | WK-33 | WK-34 | WK-35 | WK-36
[5 empty] | MD |  | Month-1 |  |  |  | Month-2 |  |  |  | Month-3 |  |  |  | Month-4 |  |  |  | Month-5 |  |  |  | Month-6 |  |  |  | Month-7 |  |  |  | Month-8 |  |  |  | Month-9
1 |  | Requirement Analysis |  |  | 57
2 |  | Design & Development |  |  | 656.5
3 |  | Testing |  |  | 155
4 |  | UAT |  |  | 142
5 |  | Documentation & Training |  |  | 85
6 |  | Delivery & Deployment |  |  | 14
7 |  | Post Go Live Support (2 Weeks) |  |  | 98
8 |  | Project Management |  |  | 96.6
|  | Roles | RC | MD | CA | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37
Resources | IS3 | Configuration Manager (CM) | 0.2 | 55 | 10 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| IS4 | Architect (AR) | 0.25 | 19 | 7.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.75 | 0.75 | 1 | 1 | 1 | 1
| IS3 | Tech Lead (TL) | 1 | 261 | 33 |  | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1
| IS2 | Sr. Developer (SD) | 1 | 279.5 | 54 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| IS1 | Jr. Developer (JD) | 3 | 222.5 | 35 | [8 empty] | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
| IS3 | Test Manager/Lead | 0.5 | 103.5 | 6 |  | 0.5 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 0.5
| IS2 | Sr. Tester (ST) | 1 | 110 | 4.5 |  |  |  | 0.5 | [9 empty] | 1 | 1 | 1 | 1
| IS1 | Jr. Tester (JT) | 3 | 127 | 11 | [13 empty] | 3 | 3 | 3 | 2
| IS1 | Technical Writer (TW) | 0.25 | 30 | 0
| IS5 | Project Manager | 1 | 96.6 | 42 | 1 | 1 | 1.5 | 1.5 | 2 | 2 | 2 | 2.5 | 2.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | Total Resource | 11.2 | 1304.1 | 203 | 1 | 6 | 8 | 7 | 4.5 | 4.75 | 4.75 | 5 | 7.5 | 7.5 | 7.5 | 5.5 | 5.5 | 10.5 | 10.5 | 10.5 | 9 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1. BRD Delivery
2. BRD Sign-off
1. Draft Manual
2. Approved Manual
3. User Training
UAT Delivery
UAT Delivery
Note on D13: Resource Count
Note on F13: Current Allocation
Note on C14: Configuration Manager
Note on C15: Architect / DB Modeler
Note on C16: Tech Lead
Note on C17: Sr. Developer
Note on C18: Jr. Developer
Note on C19: Test Manager / Lead
Note on C20: Sr. Tester
Note on C21: Jr. Tester
Note on C22: Technical Writer
Note on C23: Project Manager